## SprintTracking
Sprint# | Due Date | Assignment | Task | Person | Status
3 | 2018-10-12 | Create Complet API Specifications | make .py file and document all functionality for endpoint /Users | Kate
3 | 2018-10-13 | Create Complet API Specifications | make .py file and document all functionionality for endpoint /Book_Collections | Ani
3 | 2018-10-14 | Create Complet API Specifications | make .py file and document all functionionality for endpoint /Check_Outs | Sarah
3 | 2018-10-15 | Create Complet API Specifications | make .py file and document all functionality for endpoint /Books | Nathan
3 | 2018-10-16 | Create Complet API Specifications | Make Uml for Database structure | Nathan
2 | Oct 1 - Oct 6 |  | Establish Initial Database structure | Kate
2 | Oct 1 - Oct 6 |  | Create API for resource end points and http requests. | Sarah/Nathan
2 | Oct 1 - Oct 6 |  | Basic Testing for Interface | Ani
2 | Oct 1 - Oct 6 |  | Write Sample Test Suite
2 | Oct 1 - Oct 6 |  | Setup heroku pipeline
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Create Single Table DB for Books. Fields: BookID, BookTitle, | Kate | Pending
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Create API to handle basic HTTP requests to add book, remove book, query Book by ID, and Title | Sarah | Pending
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Create Functions to route API functions to Postgres Functions | Nathan | Pending
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Deploy to Heroku | Ani | Complete
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Plan next sprint (Thursday) | All | Complete
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Collect summaries and post Sprint review to group wiki (Thursday) | Nathan | Complete

## Backlog
Task
Authentication for users
GUID to help with sensitive information
Errors - error codes
Root endpoint - root to GET all endpoint categories that the rest api supports
HEAD - issued agains any endpoint to get just the header info.
Pagination - ?page, limit results returned to prevent dos attacks.
Schema - how to develop?