## SprintTracking
Sprint# | TimeFrame | Assignment | Task | Person | Status
2 | Oct 1 - Oct 6 |  | Establish Initial Database structure | Kate
2 | Oct 1 - Oct 6 |  | Create API for resource end points and http requests. | Sarah/Nathan
2 | Oct 1 - Oct 6 |  | Basic Testing for Interface | Ani
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Create Single Table DB for Books. Fields: BookID, BookTitle, | Kate | Pending
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Create API to handle basic HTTP requests to add book, remove book, query Book by ID, and Title | Sarah | Pending
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Create Functions to route API functions to Postgres Functions | Nathan | Pending
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Deploy to Heroku | Ani | Complete
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Plan next sprint (Thursday) | All | Complete
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Collect summaries and post Sprint review to group wiki (Thursday) | Nathan | Complete

## Backlog
Task